## Instructions
Critical Path Analysis – Spreadsheet Homework
Four tasks. In Tasks 1 to 3 you build the model yourself. Task 4 gives you a finished model to experiment with.
Colour key
Yellow = your work. Type a formula or a written answer here.
1000 | Blue = given information. Only change it when a question tells you to, then change it back.
The tasks
Tab | Context | What you practise
Task 1 Formal | Planning the Year 12 formal | Forward scan: ESTs, EFTs and the minimum completion time
Task 2 Formal backward | The same formal, continued | Successors, backward scan, float and the critical path
Task 3 Heritage project | Restoring a heritage building with the local community | A whole project: both scans, the critical path and a Gantt chart
Task 4 Garden | Building a community garden | Using a finished model to examine delays and speed-ups
Rules for a good spreadsheet model
1. Every yellow table cell must contain a formula starting with =, not a typed number.
2. Formulas must use cell references (such as $B$5) for the given values, so the model updates when a value changes.
3. Use $ signs to lock a reference before you fill a formula down or across.
4. Use the check figures on each tab to test your formulas before you answer the questions.
5. Every chart needs a title and axis titles, and a legend if it shows more than one series. Place charts to the right of the questions.
6. Written answers should include the numbers from your spreadsheet that support them.
7. In Tasks 1 to 3 you may write each EST and LFT with MAX or MIN of the right cells (for example =MAX(H6,H7)), or use VLOOKUP as in the tutorial.

## Task 1 Formal
Task 1 Planning the formal: forward scan
The formal committee has listed the activities needed to run the Year 12 formal, with how many days each takes and what must be finished first.
Precedence table | [7 empty] | What to do
Activity | Task | Duration (days) | Immediate predecessor 1 | Immediate predecessor 2 | Immediate predecessor 3 | EST | EFT | 1. Activity A is done for you: it has no predecessors, so its EST is 0, and EFT = EST + duration.
A | Book the venue | 3 |  |  |  | 0
B | Choose a theme | 2 | [5 empty] | 2. For each other activity, EST = the LARGEST EFT of its immediate predecessors. For example, E must wait for A and B, so G10 could be =MAX(H6,H7).
C | Book a DJ | 2 | A
D | Order decorations | 4 | B |  |  |  |  | 3. Fill in every EST and EFT, working down the table.
E | Sell tickets | 5 | A | B |  |  |  | 4. In C17, find the minimum completion time with MAX.
F | Arrange catering | 3 | A |  |  |  |  | Check: activity G should have EST 6 and EFT 8.
G | Decorate the venue | 2 | C | D
H | Finalise the seating plan | 1 | E | F |  |  |  | Questions – type your answers in the yellow boxes
I | Formal night | 1 | G | H |  |  |  | Q1. What is the minimum completion time for the formal?
Your calculations
Minimum completion time (days)
Q2. Which activities can start straight away? How can you tell from the table?
Q3. Explain why activity E has an EST of 3, not 2.
Q4. Booking the DJ (C) actually takes 4 days. Change C8 (then change it back). Does the minimum completion time change? Explain.

## Task 2 Formal backward
Task 2 The formal, continued: backward scan and critical path
This tab continues Task 1. The durations, ESTs and EFTs are linked to your answers there, so finish Task 1 first.
Backward scan | [10 empty] | What to do
Activity | Duration (days) | EST | EFT | Immediate successor 1 | Immediate successor 2 | Immediate successor 3 | LFT | LST | Float | Critical? | 1. Fill in the successors: for each activity, list every activity that has it as an immediate predecessor. Use the precedence table in Task 1.
2. The last activity (I) is done for you: its LFT is the minimum completion time. Work UP the table: LFT = the SMALLEST LST of its immediate successors. For example, F11 has one successor, H, so H11 could be =I13.
3. LST = LFT − duration. Float = LST − EST. In column K, use IF to show "Critical" when the float is 0.
4. Type the critical path in D18, for example A – B – C.
Check: activity D should have LST 3 and float 1.
Questions – type your answers in the yellow boxes
Your calculations | [10 empty] | Q1. Which activities are critical? Write the critical path.
Minimum completion time (from Task 1)
Critical path
Q2. Which activity has the most float, and how much?
Q3. What does the float of activity F (arrange catering) mean for the person organising the catering?
Q4. Can booking the DJ (C) be delayed by 3 days without delaying the formal? Explain using its float.

## Task 3 Heritage project
Task 3 A community heritage project
A local council is working with Aboriginal Elders, Traditional Owners and the historical society to restore an old building and open it as a cultural heritage centre. Durations are in weeks.
Precedence table | [14 empty] | What to do
Activity | Task | Duration (weeks) | Pred. 1 | Pred. 2 | Pred. 3 | Succ. 1 | Succ. 2 | Succ. 3 | EST | EFT | LFT | LST | Float | Critical? | 1. Forward scan: fill in the EST and EFT of every activity, working down. Activity A is done for you.
A | Consult Elders and Traditional Owners | 3 |  |  |  | C | D | F | 0
B | Survey the site | 2 |  |  |  | D | [8 empty] | 2. Find the minimum completion time in C18.
C | Research historical records | 4 | A |  |  | E | [8 empty] | 3. Backward scan: fill in the LFT and LST of every activity, working up from J. Then find each float and use IF to mark the critical activities.
D | Apply for heritage permits | 3 | A | B |  | G
E | Design interpretive signs | 3 | C |  |  | H | [8 empty] | 4. Type the critical path in C19.
F | Record oral histories | 5 | A |  |  | I | [8 empty] | 5. Insert a Gantt chart: select the Activity, EST and Duration columns (hold Ctrl or Cmd to select columns that are apart), insert a stacked bar chart, then format the EST series to have no fill. Reverse the order of the categories so A is at the top.
G | Restore the building | 6 | D |  |  | H
H | Install the signs | 2 | E | G |  | J
I | Build the online archive | 3 | F |  |  | J
J | Opening ceremony | 1 | H | I | [10 empty] | Check: activity F should have EST 3 and float 3.
Your calculations | [14 empty] | Questions – type your answers in the yellow boxes
Minimum completion time (weeks) | [14 empty] | Q1. What is the minimum completion time for the project?
Critical path
Q2. What is the critical path? Check that its durations add up to the minimum completion time.
Q3. Use your Gantt chart. Which activities are under way during week 8 (between time 7 and time 8)?
Q4. Which non-critical activity can be delayed the longest without delaying the opening? By how many weeks?

## Task 4 Garden
Task 4 Building a community garden: what if?
This model of a community garden build is already finished. Use it to see what happens when activities are delayed or sped up. Durations are in days.
The model – change only column D | [14 empty] | What to do
Activity | Task | Original duration | Change (days) | New duration | Pred. 1 | Pred. 2 | EST | EFT | Succ. 1 | Succ. 2 | LFT | LST | Float | Critical? | 1. Every formula in this model is already written. Read a few to see how they work.
A | Clear the site | 2 | 0 | [5 empty] | C | D
B | Order soil and plants | 4 | 0 | [5 empty] | F | [5 empty] | 2. To lengthen an activity, type the extra days in its blue Change cell in column D. To shorten it, type a negative number. The scans, float and critical path all update.
C | Build garden beds | 3 | 0 |  | A |  |  |  | E | F
D | Install irrigation | 2 | 0 |  | A |  |  |  | G
E | Lay paths | 3 | 0 |  | C |  |  |  | H | [5 empty] | 3. Set every Change cell back to 0 after each question.
F | Fill beds with soil | 1 | 0 |  | B | C |  |  | G
G | Plant seedlings | 2 | 0 |  | D | F |  |  | H | [5 empty] | Questions – type your answers in the yellow boxes
H | Mulch and put up signs | 1 | 0 |  | E | G | [8 empty] | Q1. What is the completion time? The model lists the critical activities – how many critical paths are there, and what are they?
Results
Completion time (days)
Critical activities
Q2. The soil and plants (B) arrive 3 days late. What is the new completion time? Explain using the float of B.
Q3. How many days can installing the irrigation (D) be delayed without delaying the project?
Q4. Extra volunteers can shorten ONE activity by 1 day. Which activities would make the garden finish a day earlier? Why not the others?